## 00 Read Me
Enterprise Architecture Project Impact Matrix
<client or portfolio name> ¦ Version 1.0 ¦ <date>
Purpose
Scores each proposed initiative on a consistent set of weighted dimensions so that sequencing and funding decisions can be defended in an EA forum.
Replace this text with the specific purpose for this engagement.
Every score is a starting position for review, not a decision.
Sheets
Sheet | What it is for | Who maintains it | Update cadence
01 Scoring Model | Weights and the 1 to 5 anchors. Change a weight and every project score recalculates. | Enterprise Architecture | At each portfolio review
02 Portfolio Summary | Roll-up with weighted score, rank, cost and score per $100k. The board view. | Enterprise Architecture | Automatic
03 Sequencing | Waves, cross-project dependencies, and resource contention. | EA and Delivery | At each portfolio review
04 Risk Register | All project risks with likelihood, impact and mitigation. | Enterprise Architecture | Fortnightly
05 Open Questions | What must be answered before approval, and the decision each blocks. | Engagement lead | Weekly until closed
06 Savings Case | Payback model. Fill the baseline and expected saving; payback calculates. | FinOps and EA | Monthly
07 Decision Log | What the forum decided, on what conditions, and who answers for it. | EA and Delivery | After each forum
P1 to P8 | One sheet per initiative. Delete the slots you do not use. | Project architect | Weekly during delivery
Cell conventions
Blue text | Hardcoded input. Edit these.
Green text | Link pulled from another sheet. Do not overwrite.
Black text | Calculated. Do not overwrite.
Yellow fill | Information still owed. These are the gaps that block approval.
Rules that keep this useful
Never give two initiatives the same score profile. If they score the same on every dimension, the matrix cannot rank them and has no decision value. This is the single most common failure mode.
Score against evidence, and cite the source document and section in the evidence column. A score of 3 with a named source beats a score of 5 with none.
Where no evidence exists, score conservatively and log the gap on '05 Open Questions'. Do not guess upward.
A score can be deliberately low where a proposal is weaker than it claims. Those are the most valuable cells in the workbook.
Set the weights to the prioritization lens the sponsor confirms, before scoring. Do not score first and pick the lens that gives the answer you wanted.
Owners are people, not roles. 'Security' does not approve anything; a named individual does.
Governance record
Prioritization lens | balanced | Confirmed with the sponsor before scoring.
Lens agreed by (named) | A. Example, VP Operations | The person who accepted these weights.
Lens agreed on | 2026-01-15
Risk appetite | No red risk without a named owner and a review date. | Red risks start at a score of 9.
Next review | 2026-04-15 | Re-score on a material change, or on this date.
Terms follow TOGAF and COBIT: an initiative is a work package, a wave is a transition architecture. See references/standards-mapping.md.
Document coverage
Document | What it feeds in this workbook | Level | Coverage
Proposal, business case or statement of work (PROPOSAL) | Project profile (name, sponsor, scope, deadline, status, basis); Business value and Cost assessments; the questions the proposal asks the client go to 05 Open Questions | Required, each initiative | Received for all scored initiatives
Cost and effort estimate: line items, hours by role, duration (ESTIMATE) | Cost and duration cells, score per $100k on 02 Portfolio Summary, capacity on 03 Sequencing, Delivery confidence | Required, each initiative | Received for all scored initiatives
Target-state architecture, principles and strategy (TARGET_STATE) | Strategic alignment score, section 9 (capability, principles, gap closed), gates 1 and 2 | Required, portfolio | Received
Sponsor confirmation of the prioritization lens (email or minutes) (LENS) | 01 Scoring Model weights, Governance record on the Read Me (who agreed the lens, and when) | Required, portfolio | Received
Funding envelope or budget statement, or a written 'not yet defined' (FUNDING) | 03 Sequencing (waves as approval tranches), Delivery confidence weighting | Required, portfolio | Received
Current-state architecture or inventory of the affected systems (CURRENT_STATE) | Dependencies, section 9 (gap closed), Risk reduction | Recommended, portfolio | Not provided
Current run-cost baseline: cost export, invoices, licence list (COST_BASELINE) | 06 Savings Case, KPI baselines, Cost optimization score | Recommended, each initiative or portfolio | Not provided
Incident, risk and audit history (INCIDENTS) | Risk reduction and Time criticality scores, 04 Risk Register | Recommended, portfolio | Received
Security and compliance requirements, findings and review status (SECURITY) | Security and compliance score, gates 3 and 8 | Recommended, each initiative | Not provided
Ownership and support model: named people, RACI, org chart (OWNERSHIP) | Sponsor, architecture owner, delivery owner, benefits owner, gate 4 | Recommended, portfolio | Not provided
Resource and capacity plan: named roles and availability (CAPACITY) | Capacity table on 03 Sequencing, Delivery confidence | Recommended, portfolio | Not provided
Vendor contracts, licences and renewal dates (CONTRACTS) | Time criticality, hard deadlines, consumption-billed dependencies | Recommended, portfolio | Not provided
Earlier matrices, ADRs and forum decisions (PRIOR_DECISIONS) | Consistency of scores, 07 Decision Log, gate 10 | Optional, portfolio | Not provided
Document register
Type and initiative | Document and provider | Version or date | Status
PROPOSAL / P1 | Proposal deck, event streaming for the customer feed (A. Example) | v3, 2026-01-08 | Received
ESTIMATE / P1 | Cost and effort estimate, deck slide 14 (A. Example) | v3, 2026-01-08 | Received
TARGET_STATE / ALL | Target-state architecture, section 3 (B. Example) | v2, 2025-11-20 | Received
LENS / ALL | Sponsor email confirming the balanced lens (A. Example) | 2026-01-15 | Received
FUNDING / ALL | Funding envelope not yet defined, confirmed in writing (C. Example) | 2026-01-15 | Received
INCIDENTS / ALL | Batch failure log, January to June (Platform Team) | 2026-07-01 | Received
COST_BASELINE / P1 | Run-cost export for the batch VM and storage (FinOps) |  | Requested

## 01 Scoring Model
Scoring model
Lens: balanced. Changing a weight recalculates every project sheet and the summary.
Weights
Dimension | Weight | Rationale
Business value | 20% | Whether the initiative changes a business outcome, not just a technical one.
Cost optimization and savings | 20% | Direct savings and the ability to evidence savings. An unevidenced saving cannot be booked.
Time criticality | 20% | Deadlines, vendor retirements, and problems that cost something every month they wait.
Risk reduction and resilience | 10% | Reduction in incident frequency, blast radius, or single points of failure.
Security and compliance | 10% | Net change in security posture. This can be negative.
Delivery confidence | 10% | Confidence the work lands on time and scope. Low confidence discounts a high score.
Strategic and architecture alignment | 10% | Whether it advances a target-state standard or is purely tactical.
Total | 100% | Must equal 100 percent.
Lens presets
Preset | Business value | Cost optimization and savings | Time criticality | Risk reduction and resilience | Security and compliance | Delivery confidence | Strategic and architecture alignment
balanced | 20% | 20% | 20% | 10% | 10% | 10% | 10%
run_cost | 10% | 35% | 15% | 10% | 5% | 15% | 10%
deadline_risk | 10% | 10% | 35% | 20% | 5% | 10% | 10%
delivery_speed | 15% | 10% | 15% | 10% | 5% | 35% | 10%
security | 10% | 10% | 10% | 20% | 35% | 5% | 10%
Copy a preset row into B6:B12 to switch lens. Confirm the lens with the sponsor before scoring, not after.
Score anchors, 1 to 5
Dimension |  | 1 | 2 | 3 | 4 | 5
Business value |  | No measurable business outcome; internal convenience only. | Efficiency gain for one team, no quantified baseline. | Quantified efficiency or quality gain for a defined process. | Removes a live operational blind spot or unlocks decisions across teams. | Direct revenue, contractual, or client-facing outcome.
Cost optimization and savings |  | No savings; adds run cost. | Soft labour savings only, not booked. | Modest run-cost reduction, single digit percent of the affected spend. | Material and measurable reduction, or a direct enabler of one. | Primary purpose is cost reduction with a named savings target.
Time criticality |  | No deadline. Can slip a year with no consequence. | Preferable this year, no consequence if deferred. | A live problem is costing time or risk every month it waits. | Dependency window or vendor change makes deferral expensive. | Hard external deadline or an already unsupported component.
Risk reduction and resilience |  | No change to risk posture. | Marginal improvement. | Reduces the frequency or blast radius of a known failure mode. | Removes a recurring incident cause or restores a lost safety net. | Removes a single point of failure with client-visible consequences.
Security and compliance |  | Increases attack surface with no offsetting control. | Net neutral, or new surface offset by new controls. | Minor control improvement. | Removes standing credentials, adds auditability or least privilege. | Closes an audit or regulatory finding.
Delivery confidence |  | Novel, undefined scope, unproven pattern, external dependency. | Large scope with material unknowns. | Well understood work with normal coordination overhead. | Proven pattern already running elsewhere in the estate. | Small, bounded, single team, reversible in hours.
Strategic and architecture alignment |  | Conflicts with target-state architecture. | Tactical, creates no reusable asset. | Consistent with standards, no reuse beyond itself. | Advances a target-state standard reusable by other workloads. | Establishes or completes an enterprise standard.

## 02 Portfolio Summary
Portfolio summary
Everything pulls from the project sheets. Weights come from '01 Scoring Model'.
Ranked portfolio
ID | Project | Estimated cost (USD) | Duration (months) | Weighted score | Rank | Score per $100k | Time criticality | Delivery confidence | Cost optimization | Recommended wave
P1 | EXAMPLE Replace nightly batch export with event streaming | 84000 | 3 | 3.5 | 1 | 4.1667 | 3 | 4 | 3 | Wave 1
P2 |  | 0 | 0
P3 |  | 0 | 0
P4 |  | 0 | 0
P5 |  | 0 | 0
P6 |  | 0 | 0
P7 |  | 0 | 0
P8 |  | 0 | 0
| Portfolio | 84000 |  | 3.5
How to read this
Weighted score answers how much this matters. Score per $100k answers how much we get for the money.
Replace these lines with the specific reading for this portfolio, naming initiatives.

## 03 Sequencing
Sequencing, dependencies and capacity
Recommended delivery order and the constraints that shape it
Recommended waves
Wave | Projects | Indicative window | Cost (USD) | Why this grouping | Entry condition
Wave 1 | <initiatives> | <window> | 0 | <why this grouping> | <entry condition>
Wave 2 |  |  | 0
Wave 3 |  |  | 0
Hold |  | Not scheduled | 0 | <why held rather than dropped> | <what would unhold it>
| Total |  | 0
Cross-project dependencies
From | To | Type | Strength | What it means for sequencing | Owner
Resource contention
Role | Committed across the portfolio | Peak concurrent demand |  | Constraint
Solutions Architect
DevOps / Platform Engineer
Project Manager
FinOps

## 04 Risk Register
Consolidated risk register
All project risks, ranked by initial likelihood times impact
Risks across the portfolio
ID | Project | Risk | Likelihood | Impact | Score | Mitigation | Owner | Response | Residual
R01 | P1 | Duplicate or lost records during parallel run | Medium | Critical | 8 | Run both paths against a shadow consumer group and reconcile record counts daily before cutover. | Architecture | Mitigate | 3
R02 | P1 | Event Hubs throughput unit cost not modelled | High | Medium | 6 | Model expected events per second against the pricing tier before committing. | FinOps | Mitigate | 2
R03 | P1 | Downstream consumers assume a nightly batch boundary | Medium | High | 6 | Survey each consumer for time-window assumptions during design. | PM
R04 | P1 | Batch VM decommission deferred indefinitely, so no saving lands | High | Medium | 6 | Make the decommission a named deliverable with a date, not a follow-up. | Delivery lead
Score is likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above, amber from 6. Every red risk needs a named owner and a review date before its project is approved. Response is Mitigate, Accept, Transfer or Avoid. Residual is the score once the mitigation is in place.

## 05 Open Questions
Open questions and information gaps
What is still owed, and the decision each answer unblocks
Blocking questions, in priority order
ID | Project | Area | Question | Why it matters and what it unblocks | Owner to answer | Status
Q01 | [5 empty] | Open
Q02 | [5 empty] | Open
Q03 | [5 empty] | Open
Q04 | [5 empty] | Open
Q05 | [5 empty] | Open
Q06 | [5 empty] | Open
Q07 | [5 empty] | Open
Q08 | [5 empty] | Open
Q09 | [5 empty] | Open
Q10 | [5 empty] | Open
Q11 | [5 empty] | Open
Q12 | [5 empty] | Open
Q13 | [5 empty] | Open
Q14 | [5 empty] | Open

## 06 Savings Case
Savings case and payback
Yellow cells are the inputs still owed. Everything else calculates.
Payback model
ID | Project | Build cost (USD) | Current annual run cost (USD) | Expected annual saving (USD) | Saving % | Payback (months) | Evidence position
P1 | EXAMPLE Replace nightly batch export with event streaming | 84000 | 0 | 0 |  | Awaiting baseline | EXAMPLE. Fill D and E once the baseline arrives. Payback calculates.
P2 |  | 0 | 0 | 0 |  | Awaiting baseline
P3 |  | 0 | 0 | 0 |  | Awaiting baseline
P4 |  | 0 | 0 | 0 |  | Awaiting baseline
P5 |  | 0 | 0 | 0 |  | Awaiting baseline
P6 |  | 0 | 0 | 0 |  | Awaiting baseline
P7 |  | 0 | 0 | 0 |  | Awaiting baseline
P8 |  | 0 | 0 | 0 |  | Awaiting baseline
| Portfolio | 84000 | 0 | 0 |  | Awaiting baseline
Columns D and E are the only inputs. An initiative that is a pure enabler should show zero expected saving and be argued on the grounds that it makes the other rows provable.

## 07 Decision Log
Decision log
What the forum decided, on what conditions, and who answers for it
Decisions
Ref | Project | Decision | Conditions and rationale | Decided by (named) | Date | Reference (ADR or minutes)
Decisions: Approved, Approved with conditions, Deferred, Held, Rejected. A deferred or held initiative states what would change the decision. The scores recommend; this sheet records what was decided.

## P1
P1. EXAMPLE Replace nightly batch export with event streaming
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P1
Project name | EXAMPLE Replace nightly batch export with event streaming |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | A. Example, VP Operations |  |  | Named individual required before EA approval.
Architecture owner | B. Example, Cloud Architect |  |  | Named individual required before EA approval.
Delivery owner | C. Example, Delivery Lead |  |  | Named individual required before EA approval.
Estimated cost (USD) | 84000 |  |  | Proposal deck slide 14. Line items sum correctly.
Estimated duration (months) | 3 |  |  | 3 months, two engineers plus part-time architect.
Hard external deadline | None contractual. The nightly window is already overrunning twice a week.
Current status | Proposed, awaiting approval
Recommended wave | Wave 1 |  |  | See '03 Sequencing'.
Basis of estimate | Proposal deck slides 6 and 14; batch failure log Jan to Jun 2026. |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value | 4 | 20% | 0.8 | Downstream teams currently wait until 06:00 for data that is generated continuously. Removing the wait changes when decisions can be made, not just how fast a job runs. | A. Example | Deck slide 6; batch completion times Jan to Jun.
Cost optimization and savings | 3 | 20% | 0.6 | Removes an always-on batch VM but adds Event Hubs throughput units. Net saving is real but modest and needs modelling before it is claimed. | FinOps | Deck slide 14. Throughput unit cost not in the estimate.
Time criticality | 3 | 20% | 0.6 | No deadline, but the nightly window overruns twice a week and the failure rate is trending up. | Platform Team | Batch failure log Jan to Jun 2026.
Risk reduction and resilience | 4 | 10% | 0.4 | Removes a single nightly failure point that currently takes the whole downstream chain with it. | Platform Team | Incident records, 6 occurrences in H1.
Security and compliance | 3 | 10% | 0.3 | Replaces a shared service account with managed identity. Modest control improvement. | Security | Current-state review, section 4.
Delivery confidence | 4 | 10% | 0.4 | The same pattern is already in production for a smaller feed, so this reuses a proven design. | Architecture | Existing implementation on the orders feed.
Strategic and architecture alignment | 4 | 10% | 0.4 | Advances the event-driven target state and creates a pattern other feeds can reuse. | Architecture | Target-state architecture, section 3.
Weighted priority score |  |  | 3.5 | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
Event Hubs ingestion for the customer feed |  |  |  | Other feeds beyond the customer feed
Consumer rewrite with idempotent handling |  |  |  | Downstream consumer redesign
Parallel run against the existing batch |  |  |  | Data model changes
Runbook and alert updates |  |  |  | Decommission of the batch VM (separate change)
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
Platform | Existing Event Hubs namespace |  |  | Reuse, do not recreate. Upstream diagnostic settings point at it. | Platform Team | Critical
Client team | Downstream data owners |  |  | They must confirm parity before the batch is switched off. | PM | High
Internal | P2 Cost visibility work |  |  | Supplies the run-cost baseline this project's saving is measured against. | FinOps | Medium
Resource | Solutions Architect capacity |  |  | Part time for 3 months. Check against other initiatives. | Delivery lead | Medium
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Duplicate or lost records during parallel run | Medium | Critical | 8 | Run both paths against a shadow consumer group and reconcile record counts daily before cutover. | Architecture | Mitigate (residual 3)
Event Hubs throughput unit cost not modelled | High | Medium | 6 | Model expected events per second against the pricing tier before committing. | FinOps | Mitigate (residual 2)
Downstream consumers assume a nightly batch boundary | Medium | High | 6 | Survey each consumer for time-window assumptions during design. | PM
Batch VM decommission deferred indefinitely, so no saving lands | High | Medium | 6 | Make the decommission a named deliverable with a date, not a follow-up. | Delivery lead
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
Data freshness, generation to availability | 8 hours (nightly) |  | Under 5 minutes | Pipeline telemetry | 30 days after cutover
Failed nightly runs per month | 2.3 average H1 2026 |  | 0 | Incident records | 90 days after cutover
Monthly run cost for the feed | TBC, batch VM plus storage |  | Below baseline including throughput units | Azure cost export | 60 days after cutover
Record parity, new path versus batch | Batch baseline |  | 100 percent during parallel run | Reconciliation report | During parallel run
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Met |  |  | Target-state architecture section 3 | B. Example
Architecture standards compliance | Met |  |  | Reuses the orders feed pattern | B. Example
Security review completed | Partial |  |  | Managed identity designed, formal review not recorded | Security
Operational ownership defined (named team, not a role) | Not started |  |  | Ownership after handover undefined | Platform Team
Success KPIs agreed with a measured baseline | Partial |  |  | KPIs defined; run-cost baseline outstanding | FinOps
Rollback strategy documented and tested | Met |  |  | Batch path retained until parallel run passes | Architecture
Cost model and payback agreed with FinOps | Not met |  |  | Throughput unit cost not modelled | FinOps
Data, retention and privacy position cleared | Not started |  |  | Customer data classification | Legal
Change and CAB approval path confirmed | Not started |  |  | Change window for cutover | PMO
Architecture decision recorded and traceable (ADR or decision log) | Partial |  |  | ADR drafted, not yet accepted by the architecture board | B. Example
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1 | What is the current monthly run cost of the batch VM and its storage?
Q2 | How many events per second at peak, so throughput units can be sized?
Q3 | Which downstream consumers assume a nightly batch boundary?
Q4 | Who owns the pipeline and its alerts after handover?
Q5 | Can the batch VM decommission be a named deliverable with a date?
9. Traceability and benefits
Business capability or value stream | Customer data distribution (value stream: order to insight) |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed | Event-driven by default; managed identity over shared accounts |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) | Baseline: nightly batch, 8 hour latency. Target: continuous feed, under 5 minutes. |  |  | One line: where it is today, where it ends up.
Benefits owner (named) | A. Example, VP Operations |  |  | The person who answers for the benefit after delivery.
Benefits review date | 90 days after cutover |  |  | When the KPIs above are checked against the business case.
Standards references | TOGAF Phase E/F work package; COBIT APO05, EDM02 |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P2
P2. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P2
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P3
P3. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P3
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P4
P4. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P4
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P5
P5. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P5
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P6
P6. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P6
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P7
P7. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P7
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.

## P8
P8. <project name>
Enterprise Architecture Impact Matrix
1. Project profile
Project ID | P8
Project name |  |  |  | Pulled by '02 Portfolio Summary'. Keep it in this cell.
Business sponsor | TBC |  |  | Named individual required before EA approval.
Architecture owner | TBC |  |  | Named individual required before EA approval.
Delivery owner | TBC |  |  | Named individual required before EA approval.
Estimated cost (USD) | 0
Estimated duration (months) | 0
Hard external deadline
Current status | Proposed
Recommended wave |  |  |  | See '03 Sequencing'.
Basis of estimate | TBC |  |  | Cite the document and slide or section.
2. Weighted impact assessment
Enter 1 to 5 in column B. Anchors are on '01 Scoring Model'. Column C is a link; do not edit it.
Dimension | Score (1-5) | Weight | Weighted | Assessment | Owner | Evidence and basis
Business value |  | 20%
Cost optimization and savings |  | 20%
Time criticality |  | 20%
Risk reduction and resilience |  | 10%
Security and compliance |  | 10%
Delivery confidence |  | 10%
Strategic and architecture alignment |  | 10%
Weighted priority score |  |  |  | Out of 5.00. Compare on '02 Portfolio Summary'.
3. Scope
In scope |  |  |  | Explicitly out of scope
4. Dependencies
Type | Depends on |  |  | Nature of the dependency | Owner | Criticality
5. Key risks
Risk | Likelihood | Impact | Score | Mitigation | Owner | Response (residual score)
Likelihood times impact, each 1 to 4 (Low, Medium, High, Critical). Red at 9 or above: needs a named owner and a review date. Optional 6th to 8th items per risk: response, residual likelihood, residual impact.
6. Success KPIs
KPI | Baseline |  | Target | Measurement source | Measured by
7. EA governance gates
Gate | Status |  |  | Evidence or artefact | Reviewer | Date cleared
Alignment with a named business capability | Not started
Architecture standards compliance | Not started
Security review completed | Not started
Operational ownership defined (named team, not a role) | Not started
Success KPIs agreed with a measured baseline | Not started
Rollback strategy documented and tested | Not started
Cost model and payback agreed with FinOps | Not started
Data, retention and privacy position cleared | Not started
Change and CAB approval path confirmed | Not started
Architecture decision recorded and traceable (ADR or decision log) | Not started
Valid statuses: Met, Partial, Not started, Not met, Not applicable.
8. Open questions
Q1
Q2
Q3
Q4
Q5
9. Traceability and benefits
Business capability or value stream |  |  |  | Name the capability this changes. Gate 1 depends on it.
Architecture principles addressed |  |  |  | Optional. The principles this initiative follows or tests.
Gap closed (baseline to target) |  |  |  | One line: where it is today, where it ends up.
Benefits owner (named) |  |  |  | The person who answers for the benefit after delivery.
Benefits review date |  |  |  | When the KPIs above are checked against the business case.
Standards references |  |  |  | Optional. TOGAF phase or artefact, COBIT objective IDs.